## Budget
Direct Cost | [8 empty] | Indirect Cost
Labour |  |  |  | Materials Cost |  |  |  |  | Items: | Office Supplies | Building Costs | Licenses | Other
Title | Hourly Wage ($) | Hours | Total Cost | Task | Progress | Expected Cost | Actual Cost | Under/Over | Budgeted: | 2500 | 10000 | 1000
Project Lead Engineer | 40 | 95 | 3800 | MPPT | Complete | 20 | 10.8834 | -9.1166 | Actual | 2500 | 10000 | 545
Technical Advisors | 100 | 11 | 1100 | Batteries | Complete | 25 | 19.749 | -5.251 | Under/Over | 0 | 0 | -455 | 0
Project Manager | 120 | 10 | 1200 | Battery Regulators | Complete | 15 | 10.086 | -4.914 | Total | 13045
|  | Total of All | 6100 | Output Regulators | Complete | 10 | 8.1052 | -1.8948
|  |  |  | Microcontroller/Supporting | Complete | 30 | 23.46 | -6.54
|  |  |  | Spare Parts | Complete | 100 | 130.6064 | 30.6064
Total Costs of Project ($): | 19347.89 |  |  | Total Actual Cost |  | 200 | 202.89 | 2.89
Profits ($): | 0

## Hourly rate
Week 1 | 3 | Admin | Sum | 95
Week 2 | 2.5 | Admin
Week 3 | 8 | Research
Week 4 | 7 | Research
Week 5 | 8 | Research
Week 6 | 7.5 | Research/Design
Week 7 | 2 | Admin
Week 8 | 8 | Research
Week 9 | 9 | Research/Design
Week 10 | 8 | Research/Design
Week 11 | 8 | Research/Design
Week 12 | 10 | Design
Week 13 | 10 | Design/Admin
Week 14 | 4 | Admin
Week 15
Week 16

## Materials-Parts
Item | Price per unit ($) | Units (#) | Total Price ($) | Sourcing | Ordered
Microcontroller | 5.4 | 3 | 16.2 | https://www.digikey.com/en/products/detail/seeed-technology-co-ltd/102010428/14672129 | 1 | MPPT | 10.8834 | Licenses Cost per User
Solar Panels |  | 4 | 0 |  |  | Battery Charge Regulator: | 10.086 | FUSION 360 ($) | 545
MOSFETS | 3.16 | 4 | 12.64 | https://www.digikey.com/en/products/detail/texas-instruments/CSD19505KCS/4696181 | 1 | Batterys: | 19.749
Current Sensor | 3.79 | 1 | 3.79 | https://www.digikey.com/en/products/detail/allegro-microsystems/ACS714ELCTR-20A-T/1955901 | 1 | Output Regulators | 8.1052
Resistor 453k | 0.0106 | 50 | 0.53 | https://www.digikey.com/en/products/detail/yageo/RC0603FR-07453KL/727247 | 1 | Microcontroller/Other | 23.46
Resistor 47k | 0.0086 | 50 | 0.43 | https://www.digikey.com/en/products/detail/bourns-inc/CR0603-FX-4702ELF/3784046 | 1
ADC | 1.91 | 5 | 9.55 | https://www.digikey.com/en/products/detail/microchip-technology/MCP3221A0T-E-OT/2601429 | 1
Zener Diodes 8.51 | 0.115 | 10 | 1.15 | https://www.digikey.com/en/products/detail/diodes-incorporated/DDZ9V1ASF-7/3451476 | 1
Capacitor 0.1uF | 0.04 | 50 | 2 | https://www.digikey.com/en/products/detail/yageo/CC0603JRX7R9BB104/5195188 | 1
Resitor 2K | 0.0086 | 50 | 0.43 | https://www.digikey.com/en/products/detail/bourns-inc/CR0603-FX-2001ELF/3740910 | 1
Resistor 510 | 0.0086 | 50 | 0.43 | https://www.digikey.com/en/products/detail/bourns-inc/CR0603-FX-5100ELF/3784063 | 1
Resistor 1k | 0.0086 | 50 | 0.43 | https://www.digikey.com/en/products/detail/bourns-inc/CR0603-FX-1001ELF/3593190 | 1
Capacitor 2.2nF | 0.0284 | 50 | 1.42 | https://www.digikey.com/en/products/detail/murata-electronics/GRM1885C1H222JA01D/586951 | 1
12V Boost Regulator | 0.6 | 10 | 6 | https://www.digikey.com/en/products/detail/texas-instruments/MC33063ADR/717429 | 1
Capacitor 0.01uF | 0.0148 | 50 | 0.74 | https://www.digikey.com/en/products/detail/murata-electronics/GRM155R71H103JA88D/4358119 | 1
BMS PCB | 9.49 | 1 | 9.49 | https://www.amazon.com/Anmbest-Charger-Protection-Lithium-Battery/dp/B07KSQY67X/ref=asc_df_B07KSQY67X/?tag=hyprod-20&linkCode=df0&hvadid=242055650303&hvpos=&hvnetw=g&hvrand=2673062945255465409&hvpone=&hvptwo=&hvqmt=&hvdev=c&hvdvcmdl=&hvlocint=&hvlocphy=9014271&hvtargid=pla-591113777191&th=1 | 1
Batteries | 6.99 | 4 | 27.96 | https://www.18650batterystore.com/products/samsung-50s-21700-5000mah-25a-battery?utm_campaign=859501437&utm_source=g_c&utm_medium=cpc&utm_content=201043132925&utm_term=_&adgroupid=43081474946&gclid=CjwKCAjw6p-oBhAYEiwAgg2PgmTwHFgo_zjHD7OwBrq58vTyoWO6wZ2U9hztWCMX265vNB5GjyCThRoCVN0QAvD_BwE | 1
Pchannel Fets(IdealD) | 2.41 | 12 | 28.92 | https://www.digikey.com/en/products/detail/infineon-technologies/IRF9383MTRPBF/3455047 | 1
Resistor 180 | 0.0116 | 50 | 0.58 | https://www.digikey.com/en/products/detail/bourns-inc/CR0603-JW-181ELF/3784309 | 1
1N5819 | 0.297 | 10 | 2.97 | https://www.digikey.com/en/products/detail/stmicroelectronics/1N5819/1037326 | 1
Buck Regulator for 5V and 3.3V | 0.353 | 10 | 3.53 | https://www.digikey.com/en/products/detail/diodes-incorporated/AP62150WU-7/13161380 | 1
Resistor 31.6k | 0.0086 | 50 | 0.43 | https://www.digikey.com/en/products/detail/bourns-inc/CR0603-FX-3162ELF/3783940?s=N4IgjCBcoEwAwA4CsVQAcAuUQFUB2AlhgPIBmAsgKYCGAzgK4BOlIANCPdgNbEAWAtrTYh%2BBPNgDMYAHQA2Yf2oAPSTPkBfdgFoALKhABjKKWoAbWpXYB7KAG1wCWchABddZpAw7IZrQK0MK0ZXdSA | 1
Resistor 52.3k | 0.0086 | 50 | 0.43 | https://www.digikey.com/en/products/detail/bourns-inc/CR0603-FX-5232ELF/3784077?s=N4IgjCBcoEwAwA4CsVQAcAuUQFUB2AlhgPIBmAsgKYCGAzgK4BOlIANCPdgNbEAWAtrTYh%2BBPNiQwAdAGZh-agA8J0uQF92AWgAsqEAGMopagBtaldgHsoAbXAIAbMhABdNRpAxbIZrQK0MS0ZXNSA | 1
3.3V reg LDO | 1.52 | 3 | 4.56 | https://www.digikey.com/en/products/detail/texas-instruments/TLV2217-33KVURG3/1096010 | 1
Resistor 1Meg | 0.0086 | 50 | 0.43 | https://www.digikey.com/en/products/detail/bourns-inc/CR0603-FX-1004ELF/3593195 | 1
Resistor 10K | 0.0086 | 50 | 0.43 | https://www.digikey.com/en/products/detail/bourns-inc/CR0603-FX-1002ELF/3593188 | 1
Capacitor 10uF | 0.0554 | 50 | 2.77 | https://www.digikey.com/en/products/detail/kemet/C0805C106K8PAC7800/1090830 | 1
Nickel Strips | 5.29 | 1 | 5.29 | https://www.amazon.com/0-15x6x50mm-Soldering-Capacity-Lithium-Battery/dp/B07PQP55CM/ref=asc_df_B07PQP55CM/?tag=&linkCode=df0&hvadid=366306957285&hvpos=&hvnetw=g&hvrand=13587429733543618333&hvpone=&hvptwo=&hvqmt=&hvdev=c&hvdvcmdl=&hvlocint=&hvlocphy=9014271&hvtargid=pla-790978660223&ref=&adgrpid=71490160050&th=1 | 1
Capacitor 22uf | 0.0834 | 50 | 4.17 | https://www.digikey.com/en/products/detail/kemet/C0805C226M9PAC7800/992189 | 1
Inductor 3.3uH | 1.85 | 6 | 11.1 | https://www.digikey.com/en/products/detail/coilcraft/1812PS-332JRC/21380957 | 1
Capacitor 430pF | 0.1462 | 50 | 7.31 | https://www.digikey.com/en/products/detail/kemet/C0603C431J5GAC7867/2200750 | 1
Capacitor 150uF | 0.848 | 10 | 8.48 | https://www.digikey.com/en/products/detail/samsung-electro-mechanics/CL32A157MQVNNNE/3889025 | 1
Resistor 140m | 0.1384 | 25 | 3.46 | https://www.digikey.com/en/products/detail/te-connectivity-passive-product/RLC73N2AR14FTD/19239008 | 1
Resistor 43k | 0.0122 | 50 | 0.61 | https://www.digikey.com/en/products/detail/bourns-inc/CR0603-FX-4302ELF/3784023 | 1
Resistor 5k | 0.0084 | 50 | 0.42 | https://www.digikey.com/en/products/detail/yageo/RC0402FR-075KL/5917711 | 1
Inductor 22uH | 2.39 | 3 | 7.17 | https://www.digikey.com/en/products/detail/coilcraft/MSS1038-223MLC/21381914 | 1
Inductor 1uH | 1.19 | 3 | 3.57 | https://www.digikey.com/en/products/detail/coilcraft/LPS4012-102NRC/21380910 | 1
Inductor 47uH | 1.38 | 6 | 8.28 | https://www.coilcraft.com/en-us/products/power/shielded-inductors/high-srf-power-chip/ps-fs/1812fs/1812fs-473/ | 1
0
FR4 Board |  |  | 0 | https://rogerscorp.my.salesforce-sites.com/samples/samples_public
0
SPDT switch | 0.25 | 10 | 2.5 | https://www.digikey.com/en/products/detail/texas-instruments/SN74LVC1G3157DCKR/562895
Pins | 0.119 | 10 | 1.19 | https://www.digikey.com/en/products/detail/adam-tech/PH1-07-UA/9830505 | 1
5V LDO Regulator 10 piece | 1.1 | 1 | 1.1
0
0
0
0
0
38
|  | Total: | 202.89